## Bid_Quarters
913784250
Entity | Agency | Project Type | A&E Priority | Project | Location | Amount | Bundle | AE Appointment Status | Bid Quarter | PM
DMA | Military Affairs | MAJOR REPAIR | MR-54 | Gallatin RC & FMS HVAC & Controls Repairs | Belgrade | 1282988 | 36 | A/E APPOINTED | 4Q 2024 | Chris Batson
FWP | Fish, Wildlife & Parks | CAPITAL DEVELOPMENT | FWP CD-04 | Agency Staff Housing | Statewide | 7500000 | 20 | A/E APPOINTED | 1Q 2025 | Nick Franz
FWP | Fish, Wildlife & Parks | CAPITAL DEVELOPMENT | FWP CD-03 | Beartooth WMA Facilities Upgrade | Helena | 8000000 | 20 | A/E APPOINTED | 1Q 2025 | Nick Franz
DOJ | Law Enforcement Academy | MAJOR REPAIR | MR-15 | Boiler Replacement - MLEA Admin Building | Helena | 830000 | 11 | A/E APPOINTED | 1Q 2025 | Mark Hines
DOJ | Highway Patrol | MAJOR REPAIR | MR-58 | Boulder Dorm Renovations | Boulder | 250000 | 13 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
MUS | MSU-Northern | MAJOR REPAIR | MR-45 | Campus EMS Building Controls Upgrade Project | Havre | 400000 | 26 | A/E APPOINTED | 1Q 2025 | Chris Batson
MUS | Montana State University | MAJOR REPAIR | MR-38 | Campus Heating Plant Boiler Controls Upgrade | Bozeman | 2400000 | 9 | A/E APPOINTED | 1Q 2025 | Mark Hines
MUS | MSU-Billings | MAJOR REPAIR | MR-27 | Campus Water Distribution System Upgrades | Billings | 2400000 | 19 | A/E APPOINTED | 1Q 2025 | Mark Hines
FWP | Fish, Wildlife & Parks | CAPITAL DEVELOPMENT | FWP CD-06 | Central Services Site Upgrades | Helena | 10343330 | 25 | A/E APPOINTED | 1Q 2025 | Nick Franz
MDT | Transportation | MAJOR REPAIR |  | Clearwater Junction RV Dump Station System Repair & Renovation | Greenough | 1600000 | 34 | A/E APPOINTED | 1Q 2025 | Mark Hines
MUS | Montana State University | MAJOR REPAIR | MR-36 | Cobleigh Hall Parapet Structural Repair | Bozeman | 2400000 | 15 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
MUS | UM-Western | MAJOR REPAIR | MR-42 | Elevator Repair/Replacement | Dillon | 325000 | 33 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
MUS | Flathead Lake Bio Station | CAPITAL DEVELOPMENT | CD-13 | FLBS Water and Sewer Systems | Polson | 2500000 | na | A/E APPOINTED | 1Q 2025 | Mark Hines
DLI | Labor & Industry | CAPITAL DEVELOPMENT | CD-12 | Job Service Great Falls Building Renovation | Great Falls | 5767880 | 12 | A/E APPOINTED | 1Q 2025 | Amy Pothast
FWP | Fish, Wildlife & Parks | CAPITAL DEVELOPMENT | FWP CD-02 | Makoshika Campground Improvement & Addition | Glendive | 5000000 | 45 | A/E APPOINTED | 1Q 2025 | Nick Franz
FWP | FWP / Transportation | MAJOR REPAIR |  | Miles City Train Depot Renovation | Miles City | 2000000 | 38 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
DPHHS | Mental Health Nursing Care Center | CAPITAL DEVELOPMENT | CD-33 | MMHNCC Heated Storage Unit | Lewistown | 360000 | 6 | A/E APPOINTED | 1Q 2025 | Nick Franz
DPHHS | Mental Health Nursing Care Center | MAJOR REPAIR | MR-10 | MMHNCC Key Card Entry System | Lewistown | 125000 | 6 | A/E APPOINTED | 1Q 2025 | Nick Franz
DNRC | Natural Resources & Conservation | CAPITAL DEVELOPMENT | CD-18 | NELO Fire Ready Room | Lewistown | 445491 | 6 | A/E APPOINTED | 1Q 2025 | Nick Franz
MUS | MSU-Billings | MAJOR REPAIR | MR-20 | P.E. Building Roof Replacement | Billings | 2400000 | 46 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
DOC | Pine Hills Correctional Facility | MAJOR REPAIR | MR-07 | Pine Hills Roof Replacement | Miles City | 1000000 | 7 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
DOC | Pine Hills Correctional Facility | MAJOR REPAIR | MR-32 | Pine Hills Unit F Sewer Line Replacement | Miles City | 500000 | 8 | A/E APPOINTED | 1Q 2025 | Chris Batson
MUS | University of Montana | MAJOR REPAIR | MR-18 | Priority 1 Roof Replacements | Missoula | 2425000 | 30 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
MUS | University of Montana | MAJOR REPAIR | MR-47 | Replace Electrical Equipment | Missoula | 325000 | 35 | A/E APPOINTED | 1Q 2025 | Mark Hines
MUS | University of Montana | MAJOR REPAIR | MR-29 | Replace Fire Alarms | Missoula | 780000 | 30 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
DOJ | Highway Patrol | MAJOR REPAIR | MR-17 | Roof Replacement- MHP Boulder Campus | Boulder | 1860000 | 13 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
DNRC | Natural Resources & Conservation | CAPITAL DEVELOPMENT | CD-06 | Seedling Nursery Capital Investment | Missoula | 2797320 | 18 | A/E APPOINTED | 1Q 2025 | Nick Franz
DMA | Military Affairs | CAPITAL DEVELOPMENT | CD-31 | State Disaster Warehouse | Ft. Harrison | 5704000 | 29 | A/E APPOINTED | 1Q 2025 | Chris Batson
DMA | Military Affairs | CAPITAL DEVELOPMENT | CD-24 | State Emergency Coordination Center Expansion | Ft. Harrison | 6581000 | 29 | A/E APPOINTED | 1Q 2025 | Chris Batson
MUS | University of Montana | MAJOR REPAIR | MR-22 | Upgrade/Replace Elevators | Missoula | 2498650 | 30 | A/E APPOINTED | 1Q 2025 | Paul Blumenthal
DOC | Corrections | MAJOR REPAIR | MR-08 | Eastmont HVAC System Repairs/Replacements | Glendive | 200000 | 8 | A/E APPOINTED | 2Q 2025 | Chris Batson
MUS | Montana State University | MAJOR REPAIR | MR-50 | Hamilton Hall Life-Safety System Improvements | Bozeman | 2400000 | 15 | A/E APPOINTED | 2Q 2025 | Paul Blumenthal
MUS | Montana State University | MAJOR REPAIR | MR-28 | Lewis Hall ADA Upgrades | Bozeman | 2400000 | 15 | A/E APPOINTED | 2Q 2025 | Paul Blumenthal
MUS | MSU-Northern | MAJOR REPAIR | MR-52 | Metals Technology Building Roof Project | Havre | 400000 | 23 | A/E APPOINTED | 2Q 2025 | Chris Batson
DOC | Montana State Prison | MAJOR REPAIR | MR-33 | MSP Unit F Water Supply Upgrade | Deer Lodge | 600000 | na | A/E APPOINTED | 2Q 2025 | Mark Hines
MUS | MSU-Northern | MAJOR REPAIR | MR-51 | Pershing Hall Renovation | Havre | 2400000 | 23 | A/E APPOINTED | 2Q 2025 | Chris Batson
DOA | Administration | MAJOR REPAIR | DOA MR-05 | Roof Replacement - FWP Headquarters | Helena | 289695 | 10 | A/E APPOINTED | 2Q 2025 | Russ Katherman
MUS | Montana State University | MAJOR REPAIR | MR-30 | Tietz Hall Roof Replacement | Bozeman | 1300000 | 15 | A/E APPOINTED | 2Q 2025 | Paul Blumenthal
MUS | MSU-Northern | SUPPLEMENTAL MR | SUP MR-08 | Vande Bogart Library Roof Replacement | Havre | 1000000 | 23 | A/E APPOINTED | 2Q 2025 | Chris Batson
DMA | Military Affairs | MAJOR REPAIR | MR-57 | SMART Deferred Maintenance Program | Statewide | 1500000 | na | ON HOLD | 2Q 2025 | Chris Batson
DNRC | Natural Resources & Conservation | CAPITAL DEVELOPMENT | CD-16 | Clearwater Replacement Bunkhouse | Greenough | 1189178 | 21 | A/E APPOINTED | 3Q 2024 | Amy Pothast
DOC | Montana Women's Prison | CAPITAL DEVELOPMENT | CD-14 | MWP Roof Replacement | Billings | 5000000 | 7 | A/E APPOINTED | 3Q 2024 | Paul Blumenthal
DNRC | Natural Resources & Conservation | SUPPLEMENTAL MR | SUP MR-14 | Swan Unit Office Siding & Weather Barrier | Bigfork | 397687 | 18 | A/E APPOINTED | 3Q 2024 | Nick Franz
DNRC | Natural Resources & Conservation | CAPITAL DEVELOPMENT | CD-17 | Anaconda Bunkhouse | Anaconda | 1180962 | 21 | A/E APPOINTED | 3Q 2024 | Amy Pothast
DNRC | Natural Resources & Conservation | CAPITAL DEVELOPMENT | CD-19 | CLO Dispatch Center Expansion | Helena | 545000 | 25 | A/E APPOINTED | 3Q 2024 | Nick Franz
MUS | Flathead Lake Bio Station | MAJOR REPAIR | MR-23 | FLBS Roof Replacements | Polson | 262000 | 21 | A/E APPOINTED | 3Q 2024 | Amy Pothast
DMA | Military Affairs | MAJOR REPAIR | MR-55 | HAFRC Lighting and Control Modifications | Ft. Harrison | 351715 | 36 | A/E APPOINTED | 3Q 2024 | Chris Batson
DNRC | Natural Resources & Conservation | MAJOR REPAIR | MR-41 | Stillwater Unit Shop | Olney | 1214837 | 18 | A/E APPOINTED | 3Q 2024 | Nick Franz
MUS | MAES - BART Farm | MAJOR REPAIR | MR-53 | BART Demolition Project | Bozeman | 400000 | 39 | A/E APPOINTED | 3Q 2025 | Nick Franz
MUS | MAES - BART Farm | CAPITAL DEVELOPMENT | CD-30 | BART Life-Safety & Programmatic Improvements | Bozeman | 10000000 | 39 | A/E APPOINTED | 3Q 2025 | Nick Franz
MDT | Transportation | CAPITAL DEVELOPMENT | MDT CD-01 | Combination Facility Great Falls | Great Falls | 12600000 | 31 | A/E APPOINTED | 3Q 2025 | Nick Franz
MDT | Transportation | CAPITAL DEVELOPMENT | MDT CD-02 | Combination Facility Kalispell | Kalispell | 11000000 | 31 | A/E APPOINTED | 3Q 2025 | Nick Franz
MDT | Transportation | CAPITAL DEVELOPMENT | MDT CD-03 | Combination Facility Missoula | Missoula | 10500000 | 31 | A/E APPOINTED | 3Q 2025 | Nick Franz
MUS | MAES - Red Bluff Ranch | MAJOR REPAIR | MR-49 | Lambing Barn Renovation & Safety Upgrades | Norris | 200000 | 39 | A/E APPOINTED | 3Q 2025 | Nick Franz
DMA | Military Affairs | CAPITAL DEVELOPMENT | CD-22 | Helena Readiness HVAC & Temp Control Upgrade | Ft. Harrison | 3340668 | 36 | A/E APPOINTED | 4Q 2024 | Chris Batson
DOC | Montana Women's Prison | MAJOR REPAIR | MR-31 | MWP Perimeter Fence/Dog Yard | Billings | 1000000 | 7 | A/E APPOINTED | 4Q 2024 | Paul Blumenthal
DOC | Corrections | MAJOR REPAIR | MR-19 | DOC Develop Facility Specific Program & Master Plan | Helena | 600000 | na | A/E APPOINTED | CONTRACTOR NOT REQUIRED | Marina Little
DOJ | Justice | MAJOR REPAIR | MR-25 | Missoula Crime Lab Expansion Feasibility Study | Missoula | 75000 | 14 | A/E APPOINTED | CONTRACTOR NOT REQUIRED | Mark Hines
MUS | Great Falls College | MAJOR REPAIR | MR-05 | Fire Suppression System Upgrades | Great Falls | 500000 | na | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Mark Hines
DMA | Military Affairs | MAJOR REPAIR | MR-34 | Gallatin Readiness Center Roof Replacement | Belgrade | 1482910 | 36 | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Chris Batson
MUS | Montana State University | MAJOR REPAIR | MR-13 | Barnard Hall Cooling System Repair & Improvements | Bozeman | 1750000 | 9 | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Mark Hines
MUS | UM-Western | MAJOR REPAIR | MR-46 | Campus Building Envelope Repairs | Dillon | 415000 | 33 | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Mark Hines
MSDB | School for the Deaf & Blind | MAJOR REPAIR | MR-04 | Campus Security Camera Install | Great Falls | 300000 | na | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Mark Hines
MSDB | School for the Deaf & Blind | MAJOR REPAIR | MR-12 | Create Bus Loop and Update Parking Lot | Great Falls | 349637 | 12 | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Amy Pothast
DOA | Administration | MAJOR REPAIR |  | Data Center Roof Replacement | Helena | 700000 | na | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Paul Blumenthal
MUS | MSU-Northern | MAJOR REPAIR | MR-48 | Electronics Tech HVAC & Lighting Upgrade | Havre | 800000 | 26 | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Chris Batson
DOA | Administration | CAPITAL DEVELOPMENT | CD-20 | Old Board of Health Renovation | Helena | 3500000 | na | A/E APPOINTED | CONTRACTOR UNDER CONTRACT | Kledia Colenso
MUS | University of Montana | AUTHORITY CD | AO CD-05 | Liberal Arts Building / Eck Hall | Missoula | 4000000 | na | A/E APPOINTED | DELEGATED TO UM | Jameel Chaudhry
MUS | University of Montana | AUTHORITY CD | AMENDMENT AO-01 | McGill Hall Expansion | Missoula | 3000000 | 30 | A/E APPOINTED | DELEGATED TO UM | Jameel Chaudhry
MUS | Montana Tech | MAJOR REPAIR | MR-26 | Electrical Distribution - Multiple Bldgs. | Butte | 650000 | 37 | A/E APPOINTED | GCCM RFQ/RFP 4Q 2024 | Mark Hines
MUS | Montana Tech | CAPITAL DEVELOPMENT | CD-28 | Engineering Hall Full Interior Renovations | Butte | 8000000 | 37 | A/E APPOINTED | GCCM RFQ/RFP 4Q 2024 | Paul Blumenthal
MUS | Montana Tech | AUTHORITY CD | AO-CD-09 | Highlands College Indoor Pole Barn | Butte | 2000000 | 37 | A/E APPOINTED | GCCM RFQ/RFP 4Q 2024 | Paul Blumenthal
MUS | Montana Tech | CAPITAL DEVELOPMENT | CD-29 | Main Hall Remodel and Renovation | Butte | 30000000 | 37 | A/E APPOINTED | GCCM RFQ/RFP 4Q 2024 | Paul Blumenthal
MUS | Montana Tech | MAJOR REPAIR | MR-40 | Masonry Repairs | Butte | 455000 | 37 | A/E APPOINTED | GCCM RFQ/RFP 4Q 2024 | Paul Blumenthal
MUS | Montana Tech | MAJOR REPAIR | MR-37 | Restroom Renovations | Butte | 1200000 | 37 | A/E APPOINTED | GCCM RFQ/RFP 4Q 2024 | Paul Blumenthal
MUS | University of Montana | CAPITAL DEVELOPMENT | CD-25 | Clapp Building Renovation | Missoula | 37000000 | 28 | A/E INTERVIEWS SCHEDULED | GCCM RFQ/RFP Q4 2024 | Paul Blumenthal
DOA | Administration | MAJOR REPAIR | DOA MR-01 | Boiler & Chiller Replacement - Walt Sullivan | Helena | 473707 | 10 | A/E APPOINTED | GCCM SELECTED | Russ Katherman
DOA | Administration | MAJOR REPAIR | DOA MR-02 | Elevator Modifications - Cogswell Building | Helena | 768757 | 10 | A/E APPOINTED | GCCM SELECTED | Russ Katherman
DOA | Administration | MAJOR REPAIR | DOA MR-03 | Elevator Modifications-Walt Sullivan Building | Helena | 379763 | 10 | A/E APPOINTED | GCCM SELECTED | Russ Katherman
MUS | Montana State University | AUTHORITY CD | AO CD-02 | Gianforte Hall MSU Computing Building | Bozeman | 50000000 | na | A/E APPOINTED | GCCM SELECTED | Russ Katherman
DOC | Montana State Prison | MAJOR REPAIR | AO MR-02 | MCE Food Factory Emergency Generator | Deer Lodge | 100000 | tbd | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | AUTHORITY CD | AO CD-08 | MCE Motor Vehicle Blg: Ventilation and Paint & Sandblasting Booths | Deer Lodge | 590000 | tbd | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | MAJOR REPAIR | AO MR-03 | MCE Industries Repairs | Deer Lodge | 700000 | tbd | A/E APPOINTED | GCCM SELECTED | Mark Hines
DPHHS | Montana State Hospital | CAPITAL DEVELOPMENT | CD-01 | MSH All Compliance Upgrades for Recertification & Deferred Maintenance | Warm Springs | 15903000 | 3 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | CAPITAL DEVELOPMENT | CD-21 | MSP Check Point Bldg / Wallace Entry Security Enhancements | Deer Lodge | 3000000 | 1 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | CAPITAL DEVELOPMENT | CD-08 | MSP Entry/Staff Services Addition to Wallace Building | Deer Lodge | 12800000 | 1 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | CAPITAL DEVELOPMENT | CD-11 | MSP New Multi-Purpose Programs Building | Deer Lodge | 9000000 | 1 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | MAJOR REPAIR | MR-03 | MSP Perimeter Fence Enhancement | Deer Lodge | 1500000 | 1 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | MAJOR REPAIR | MR-02 | MSP Red Light/Emergency Notification System | Deer Lodge | 1000000 | 1 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | CAPITAL DEVELOPMENT | CD-02 | MSP Replace Low-Side Housing | Deer Lodge | 156000000 | 1 | A/E APPOINTED | GCCM SELECTED | Marina Little
DOC | Montana State Prison | CAPITAL DEVELOPMENT | CD-09 | MSP Replace Roofs | Deer Lodge | 5600000 | 1 | A/E APPOINTED | GCCM SELECTED | Paul Blumenthal
DOC | Montana State Prison | MAJOR REPAIR | MR-35 | MSP Site Infrastructure Study | Deer Lodge | 300000 | 1 | A/E APPOINTED | GCCM SELECTED | Mark Hines
DOC | Montana State Prison | CAPITAL DEVELOPMENT |  | MSP Unit D Renovation | Deer Lodge | 18840831 | 1 | A/E APPOINTED | GCCM SELECTED | Mark Hines
DOC | Montana State Prison | CAPITAL DEVELOPMENT | CD-07 | MSP Water Line Replacement | Deer Lodge | 3000000 | 1 | A/E APPOINTED | GCCM SELECTED | Mark Hines
DOA | Administration | CAPITAL DEVELOPMENT | CD-04 | Renovation of Capitol Complex Offices (ROWS) | Helena | 50000000 | 10 | A/E APPOINTED | GCCM SELECTED | Russ Katherman
DOA | Administration | MAJOR REPAIR | DOA MR-04 | Roof & Mechanical - DPHHS 111 N. Sanders St. | Helena | 1309099 | 10 | A/E APPOINTED | GCCM SELECTED | Russ Katherman
DOC | Corrections | CAPITAL DEVELOPMENT | CD-10 | Xanthopoulos Building Repairs | Warm Springs | 2950000 | 3 | A/E APPOINTED | GCCM SELECTED | Marina Little
MUS | Montana State University | AUTHORITY CD | AO CD-01 | Mark and Robyn Jones MSU College of Nursing | Bozeman | 92000000 | na | A/E APPOINTED | GCCMS SELECTED | Marina Little
DOA | Administration | MAJOR REPAIR | MR-44 | FCA Baseline Assessments | Statewide | 1500000 | 16 | A/E APPOINTED | CONTRACTOR NOT REQUIRED | Steve Faherty
DLI | Labor & Industry | MAJOR REPAIR | MR-06 | Billings UI Call Center Repairs | Billings | 1000000 | na | ON HOLD | ON HOLD | ON HOLD
DOA | Administration | MAJOR REPAIR | MR-01 | Parking Garage Repairs - 5 Last Chance Gulch | Helena | 1808145 | na | ON HOLD | ON HOLD | Bob Warfle
DMA | Military Affairs | CAPITAL DEVELOPMENT | DMA CD-04 | Ready Building Addition | Ft. Harrison | 4700000 | na | ON HOLD | ON HOLD | Chris Batson
DOC | Montana Women's Prison | MAJOR REPAIR | MR-14 | MWP Cooling System Upgrade | Billings | 750000 | 8 | A/E APPOINTED | PROJECT BID | Chris Batson
DOC | Montana Women's Prison | MAJOR REPAIR | MR-24 | MWP Heating System Upgrade | Billings | 1500000 | 8 | A/E APPOINTED | PROJECT BID | Chris Batson
DMA | Military Affairs | CAPITAL DEVELOPMENT | CD-15 | Billings Readiness and Innovation Campus (BRIC) | Billings | 78840000 | 46 | A/E APPOINTED | TBD | Chris Batson
MUS | Montana State University | MAJOR REPAIR | MR-39 | Emergency Water System & Fixture Upgrades | Bozeman | 2400000 | 9 | A/E APPOINTED | TBD | Mark Hines
DOA | Administration | MAJOR REPAIR | MR-16 | Original Governor's Mansion Repairs | Helena | 600000 | 17 | A/E APPOINTED | TBD | Amy Pothast
MUS | UM-Western | MAJOR REPAIR | MR-21 | Repair/Replace Sewer Mains | Dillon | 125000 | 33 | A/E APPOINTED | TBD | Mark Hines
MUS | MAES - Western Ag Research Center | MAJOR REPAIR | MR-43 | WARC Shop Renovation & Safety Upgrades | Corvallis | 600000 | 39 | RFQ 3Q 2024 | TBD | Nick Franz
MUS | Helena College | CAPITAL DEVELOPMENT | CD-23 | Acquire and Renovate Airport Hangar | Helena | 3600000 | na | TBD | TBD | Nick Franz
DOC | Montana State Prison | CAPITAL DEVELOPMENT |  | Flathead County Pre-release Center - Amounts includes purchase of property | Kalispell | 7000000 | na | TBD | TBD | Russ Katherman
MUS | MSU-Northern | CAPITAL DEVELOPMENT | AMENDMENT | MSU-N Health & Recreation Complex | Havre | 25000000 | 41 | TBD | TBD | Paul Blumenthal
|  | CAPITAL DEVELOPMENT | SUP-CD-09 | MAES Research Labs | Multiple | 10396000 | na | RFQ 3Q 2024 | TBD | Nick Franz
|  | CAPITAL DEVELOPMENT | CD-03 | Behavioral Health Initiative | TBD | 75000000 | 43 | RFQ 4Q 2024 | TBD | TBD
|  | CAPITAL DEVELOPMENT | AMENDMENT | Gallatin College | Bozeman | 23500000 | 40 | TBD | TBD | TBD

## Emp
Employee
Bob Warfle
Chris Ames
Chris Batson
Cody Mitchell
Kledia Colenso
Marina Little
Mark Hines
Nick Franz
Paul Blumenthal
Randy Stephens
Rick Hilmes
Russ Katherman
Steve Faherty