# Architecture & Engineering Division

# 6-Year Plan Guidance for Agencies

## Introduction: Purpose of the 6-Year Plan

A 6-year capital improvement plan (CIP) helps agencies and universities strategically plan for future facility needs by identifying, prioritizing, and scheduling capital projects over a multi-year horizon. This forward-looking approach ensures that infrastructure investments align with long-term goals, anticipated growth, and available funding. It also supports data-driven decision-making and strengthens the justification for legislative funding requests by demonstrating a clear, proactive planning process.

The 6-Year Capital Development Facilities Strategic Plan is also a statutory requirement under Section 17-7-202, MCA, as amended by House Bill 5 (2025 Session). Each state agency and institution must submit this plan to the Department of Administration’s Architecture & Engineering (A&E) Division as part of the Long-Range Building Program (LRBP).

The plan strengthens statewide capital planning and provides the Legislature with a consistent view of agency facility needs. Specifically, it:

- Identifies major repair and capital development projects early.

- Ensures projects are scheduled for the appropriate legislative funding session.

- Establishes a clear priority framework for each agency’s projects.

- Supports the Governor’s budget recommendations and the LRBP bill presented to the Legislature.

Agencies are required to submit their 6-Year Plans to A&E by April 1 of the year preceding the legislative session. Submissions are compiled and included in the statewide LRBP process.

## Instructions for Completing the 6-Year Plan (2025 Template)

### 1. Getting Started

- Open the file 6-Year Plan 2025.xlsx provided by A&E.

- Begin on the CIP Summary worksheet. This is the starting point for entering agency information and establishing the plan year schedule.

- Complete the Agency, Prepared By, and Date of Plan fields. The Date of Plan automatically determines the session schedule for all plan years.

## CIP Summary – Cover Page and Plan Overview

The Plan Summary updates automatically as projects are added or modified in the Project Entry sheet, ensuring that total estimated costs by year remain current.

### Purpose of the CIP Summary Sheet

The CIP Summary sheet serves as the cover page and summary section for the 6-Year Plan template. It provides general agency information and a consolidated summary of total project costs for each year of the plan.

### Agency Information Section

At the top of the CIP Summary sheet, agencies must complete the following fields:

| Field | Description |
| --- | --- |
| Agency: | Enter the full agency or campus name (e.g., Department of Administration). |
| Prepared By: | Enter the name of the person preparing or submitting the plan. |
| Date of Plan: | Enter the date the plan is completed or last updated. This date drives the legislative session schedule shown below in the summary section. |

### Date of Plan and Session Logic

- The Date of Plan field determines how the legislative sessions and years populate in the Plan Summary section.

- Legislative sessions begin January 1 of odd-numbered years.

- Year 1 automatically aligns with the next legislative session following the date entered.

- Each subsequent plan year advances the session number and biennium automatically.

- Example: If the Date of Plan is any time in 2025, the schedule will show:

  - Year 1 → 70th (2027–2028)

  - Year 2 → 71st (2029–2030)

  - Year 3 → 72nd (2031–2032), etc.

### Plan Summary (Total Estimated Costs by Year)

The Plan Summary table provides a roll-up of all project requests from the Project Entry sheet. Values in the table automatically update as projects are entered or modified.

### 2. Entering Project Information

Complete the following fields for each project:

- Plan Year (Col A): Enter a number 1–6 to indicate when the project should be funded. Year 1 corresponds to the next legislative session, the 70th session (2027–2028).

- Project Location / Campus (Col B): For universities, enter the university or affiliate (e.g., MSU Northern, UM Western). For agencies, enter the campus or city. Ensure names are consistent.

- Building (Col C): Enter the facility or site name.

- Project Title (Col D): Provide a clear, descriptive title (e.g., Roof Replacement – Ft. Harrison Building 530).

- Project Description (Col E): Provide a brief description of the project scope.

- Agency Priority (Col F): Rank 1–n for each session.

- Estimated Cost (Col H): Enter total project cost.

- Estimate Cost Year (Col I): Enter the year the estimate was prepared.

- Estimate Source (Col J): State the cost source (Architect/Engineer, contractor quote, RSMeans, etc.).

- Project Type (Col K): (Dropdown list) Choose one (New Construction / Additions, Renovation / Modernization, Deferred Maintenance, Infrastructure / Utilities, Property Acquisition).

- Deficiency / Issue (Col L): (Dropdown list) Identify the issue addressed by the project.

- Priority Class (Col M): (Dropdown list) Define urgency: Class 1 – Critical, Class 2 – Required Renewal, Class 3 – Strategic.

### 3. Project Classification Framework

When defining a project, consider the following steps:

Step 1 – Project Type (WHAT is being done): Select from the five types listed above.

Step 2 – Project Category (WHY it is needed): Options include Immediate Life & Safety, Damage / Wear-out, Codes / Compliance / Standards, Energy & Operational Efficiency, and Renovation & Enhancements.

Step 3 – Project Criticality (WHEN it is needed): Class 1 – Critical, Class 2 – Required (Renewal), Class 3 – Strategic.

Example: Replacing a failing steam line = Infrastructure/Utilities (Type), Damage/Wear-out (Category), Class 1 – Critical (Criticality).

### 4. Automatic Calculations (Do Not Overwrite)

LRBP Category (Col N) auto-classifies projects:

- New Construction/Additions ≥ $250,000 → Capital Development

- New Construction/Additions < $250,000 → Major Repair

- Property Acquisition → Capital Development

- Renovation/Modernization, Deferred Maintenance, Infrastructure/Utilities < $2,500,000 → Major Repair

- Renovation/Modernization, Deferred Maintenance, Infrastructure/Utilities ≥ $2,500,000 → Capital Development

### 5. Reviewing and Verifying Data

- Session Summary tab: Summarizes projects by Plan Year and Building. Refresh data after changes (Data > Refresh All).

- Agency Priority tab: Lists projects by category within each plan year and displays them in order of importance.

- CIP Summary tab: Confirms total costs by year and category; updates automatically as projects are entered.

### 6. Submitting the Plan

- Review all entries for accuracy and completeness.

- Ensure formulas are intact and not overwritten.

- Save the file with your agency name (e.g., “DOA_6YearPlan_2025.xlsx”).

- Submit the completed workbook by April 1, 2026

- Email completed 6-Year Plan to sfaherty@mt.gov

- You will receive an email confirming the plan has been received.

### 7. Support and Questions

Contact: Steve Faherty

Email: sfaherty@mt.gov Phone: (406) 422-2080